## Charter
| Project Charter |  |  |  | ING DIRECT Confidential
Instructions
|  | Project Name | Investment Sybase IQ Upgrade and Device Size Change |  |  | Provide the name of the project
|  | Corporate Program |  |  |  | Corporate initiatives this project supports
Project Organization | [5 empty] | (drop down) | Project Organization | Executive Sponsor | Business Sponsor | Senior User | Senior Supplier | Project Manager
|  | Business Sponsor | Garrett Silver |  |  | #REF! | Identify the key members of the project team. Use the drop down above for more detail: | Executive Sponsor is responsible for project governance and critical project decisions including: · charter approval & prioritization · resolving any project related issues that are escalated to them · approving closure of the project | Identify the Business Sponsor responsible for: · Achieving the goals and objectives of the project · Communicating project status beyond the project team · Funding/budget · Approving spend | Identify the Sr. User responsible for: · Documenting and gathering business requirements across all affected areas · User Acceptance Testing · Manage requirements change requests | Identify the Sr. Supplier responsible for: · Managing resources required to produce project deliverables · Documenting technical specifications and coordinating across all suppliers. · Estimates of effort and costs to produce project deliverables | Identify the Project Manager responsible for managing all phases of the project: · Start Up & Planning · Execution & Tracking · Quality Assurance · Delivery · Closure
|  | Business Owner | Sean Jacobsen
|  | Senior Users | Matt McArthur, Bob Miller, Jurie Pieterse Brandon Potter | [11 empty] | Maximize Throughput | IT will continue adopting Agile processes in Development and Infrastructure to drive attention to the highest business value activities. Continuous integration efforts will be extended to include Lending and Investment code builds and deployments.
|  | Senior Suppliers | Larisa Brown | [11 empty] | Strategic Projects | IT’s primary focus in 2009 will be on the timely delivery of projects within the following business areas: Mortgage Systems, Fraud Systems, Security Systems, Orange Data Warehouse, Electric Orange 2.0, ShareBuilder Sybase Upgrade and Mutual Funds Platform.
|  | Project Manager | Karen Grose | [11 empty] | Systems Continuity | After completing ShareBuilder’s full disaster recovery build-out, IT will concentrate on finishing all remaining tasks to enable running our Bank operations for 24 hours from our secondary data center along with recovering back to our primary data center with minimal downtime. To date, our DR tests have been successful but without real life constraints and volumes.
|  | Technical Product Owner | Larisa Brown
|  | Portfolio Manager | Matt Watson
[15 empty] | Unify Customer Experience | With the convergence of Bank and ShareBuilder customers, IT will support initiatives that minimize variations of customer experiences with these areas: websites, marketing campaigns, account funnels (authentication controls and know your customer) and call centers.
[15 empty] | Web Customer Behavior Management | Since the majority of our customer interactions are web-based, IT will drive for more comprehensive website behavior tracking through greater utilization of our existing toolsets with extra attention paid on increasing our account funnel conversion rates, simplicity and error free experiences.
Business Case | [5 empty] | (drop down) | Business Case | Business Area | Project Purpose | Project Scope & Deliverables | Alternative Options / Scenarios | Recommendation | Success Criteria | Intangible Benefits
| Vertical |  |  |  |  | #REF! | The Business Case section of the charter should be completed by the business sponsor. Use the drop down above for specific help. | The business area is the department that the project 'rolls up' to. This field also allows write-ins. | Provide an explanation of why this project is necessary, include the following: * Background, history or context that may help evaluate the case for this initiative. * External factors (e.g. increased competition, regulatory compliance * Internal factors (e.g. policy changes, corporate directives, etc.) * Other important related projects, programs, plans | Outline the various options that have been considered to deliver the required outcome. | The alternative options/scenarios story may be told with information drawn from business plans, vendor proposals, pilot studies. All the scenario elements should tell the story of one possible future, in concrete detail. | Provide explicit recommendations. * Approval of $0.00 in CapEx funding for … * Implementation of this proposal to commence in mm/yyyy and complete in mm/yyyy.> | Provide explicit goals w/ metrics. This project will be considered successful when: * The following major functionality implemented * The following benefits are realized * The following new/changed processes are operationalized | State the benefits clearly and in as measurable a form as possible
|  | IT Infrastructure |  |  |  |  | 10 | 0 | 3 | 11 | 19 | 27 | 35 | 43
Categorization
Project
Project Purpose
The purpose of this project to upgrade our current IQ databases to a Sybase supported version of IQ. Our current version of IQ is no longer supported by Sybase and presents significant risk for outage. Along with the upgrade to the new version we will also migrate the current devices to larger devices. This will enable us to accommodate increased capacity, waste less space in device overhead and gain stability. In addition to our IQ software, the hardware used by IQ databases will soon be at end of life. We will use the upgrade as an opportunity to refresh the hardware to provide increased performance, stability and capacity. Finally we will reduce the cost of servers and maintenance by removing the HA IQ database server in each of the data centers. We will achieve this by creating a process and the changes necessary to run IQ in the Prod B data center.
Project Scope & Deliverables
Scope: 1. Re-architect SAN optimum device size, Migrate the data from the old devices to the new devices 2. Install and configure two new IBM P750s to house the production IQ databases (warehouse and datamart). 3. Optimize the network channel and disk array for the larger device size 4. Upgrade IQ to version 15.2 in development, QA and prod environments 5. Migrate non catalog data to a non System-Main dbspace. If ETL benchmarks indicate increased run time we will not migrate ETL tables to another dbspace. 6. Provide a process and changes that enable us to run DSS in Prod B. 7. Security scan of servers after the upgrade 8. Add required 4 new Dev/QA Sybase CPU IQ licenses 9. Remove two standby Production IQ licenses Deliverables: 1. 2 P750s built and configured for production 2. IQ DSS warehouse and datamart databases upgraded to version 15.2 using larger device sizes A. DE Production B. MN Production C. WA Dev D. MN QA 3. Analysis of ETL components and possible move to new dbspace 4. User data stored in the System-Main dbspace moved to new dbspace 5. Process and changes needed to run DSS in a Prod B environment.
Alternative Options / Scenarios
1. Upgrade IQ on the current platform to version 15.2 and migrate the data to larger devices using an ING Direct Investing written ETL process 2. Upgrade IQ on the current platform to version 15.2 and migrate the data to larger devices using the Sybase migration product 3. Remain on the unsupported version 4. Upgrade to 15.2 and migrate to new devices on a Linux platform using an ING Direct Investing written ETL process 5. Upgrade to 15.2 on the current platform and do not increase the device size and increase the number of devices using the same size 6. Migrate to another DBMS and platform
Recommendation
The recommendation is to upgrade production IQ on the current platform to version 15.2 and migrate the data to larger devices using an ING Direct Investing written ETL process. The stability of the current environment is an issue. Upgrading and moving to larger devices will allow us to quickly migrate to a supported software version, make the best use of the space currently allocated without additional SAN procurement. By creating the process and ability to run IQ in the Prod B data center we will provide HA for IQ without the cost of an additional dedicated server in each of the data centers.
Success Criteria
1. All production Sybase IQ databases upgraded to a supported version 2. Successful migration of all production IQ data to the new devices
Intangible Benefits
Migrating to larger devices should make better use of the space allocated and may increase throughput. We will no longer need the SAN that is attached to the two HA IQ database servers (2 TB in DE and MN).
Financial Summary
Project Costs
|  |  | CapEx | OpEx | Total
Bank
|  | Internal | 17640 | 0 | 17640
|  | External | 0 | 0 | 0
|  | Future Cost Commitments | 0 | 0 | 0
|  | Sub-Total | 17640 | 0 | 17640
Brokerage
|  | Internal | 228060 | 0 | 228060
|  | External | 332810.9243 | 52602 | 385412.9243
|  | Future Cost Commitments | 0 | 89529.6178 | 89529.6178
|  | Sub-Total | 560870.9243 | 142131.6178 | 703002.5421
Amendment 1
|  | Internal | 0 | 0 | 0
|  | External | 0 | 0 | 0
|  | Future Cost Commitments | 0 | 0 | 0
|  | Sub-Total | 0 | 0 | 0
|  | Total | 578510.9243 | 142131.6178 | 720642.5421
Total External Spend
|  | Bank | 0 | 0 | 0
|  | Brokerage | 332810.9243 | 52602 | 385412.9243
|  | Amendment 1 | 0 | 0 | 0
|  | Total | 332810.9243 | 52602 | 385412.9243
Tangible Benefits
|  | Revenue Generation | This project is cost of doing business and is required in order to provide ING Investment Inc. with Sybase IQ support. ING Investment Inc.uses Sybase IQ for the DSS data warehouse. |  | 0
|  | Cost Efficiency |  |  | 0
|  | Cumulative Benefits |  |  | 0
Financial Summary
|  | Net Present Value |  |  | -701730.1553
|  | Discounted ROI |  |  | -100%
|  | Payback in Years |  |  | After Year 3
MTP Budget
|  | MTP CapEx $ | <Not Budgeted> | MTP OpEx $ | <Not Budgeted>
Project Schedule
|  | Desired Start Date | 2011-06-15 |  |  | Indicate when the project should start and finish, also indicate any critical dates: regulatory, compliance, year-end, etc.. and what affect there will be if the schedule is not met
|  | Desired End Date | Sept. 30, 2011
Critical Time Constraints
We are on an unsupported product and soon will be on hardware that has reached end of life so it is critical to complete this project as soon as possible.
Impact if not met
Team is required to fix IQ issues without Sybase support.
Vertical Commitments
IT Shared Applications and Architecture Shared Services Network Security Shared Services Security Shared Services Backups Shared Services Storage IT Infrastructure DBA Server Architecture IT Process Management Investment Services Back-office Reporting
Risks
|  | Risks to the Business | Impact | Probability | Response
|  | If the DBAs encounter a DBMS issue they cannot resolve a prolonged outage could occur | High | Low | Although there have been issues our DBAs have been able to resolve issues to-date
|  | Risk | Impact | Probability | Responses
|  | Risk | Impact | Probability | Responses
|  | Risk | Impact | Probability | Responses
|  | Risks to the Project | Impact | Probability | Response
|  | Resources may have conflicting production support and project responsibilities | High | High | The project will need to be pushed to accommodate conflicting priorities or a priority for this effort will need to be established
|  | Risk | Impact | Probability | Responses
|  | Risk | Impact | Probability | Responses
|  | Risk | Impact | Probability | Responses
Touch Points
|  | Vertical | Contact
|  | Back Office & Reporting | X
Consumer Lending
Corporate Facilities
|  | Deposit Operations |  |  |  | Indicate what the Touch Points of the project are - what departments need to be included in discussions and departments will be impacted by this project
Customer Security & Fraud Prevention
Deposit Services
|  | Investment Services | X
|  | IT Infrastructure | X
|  | IT Technology Services | X
Lending - Credit and Underwriting
Lending - Customer
Lending - Origination Operations
Lending - Servicing & Default Servicing
Sales
|  | Self Service / Mobile |  |  |  | Additionally, indicate any committees to whom the project will require approval from, input from, or input to.
Senior Management Signoff
Arkadi Kuhlmann
Jim Kelly
Rudy Wolfs
John Bone
Dan Greenshields
Bill Higgins
Stephan Klee
John Mason

## Bank Costs
Project Charter | [14 empty] | ING DIRECT Confidential
Investment Sybase IQ Upgrade and Device Size Change
Cost Summary | [13 empty] | To specify additional year spend, expand columns I-L using the plus sign above column M. For Office 2003 Users: To amend the cost section, unhide the "Cost - Amendment 1" sheet by selecting the Format menu, opening the Sheet sub-menu, and selecting unhide. For Office 2010 Users: Right clicking on any tab and selecting unhide brings up a sub-menu of hidden worksheets. Select AMD 1 Costs un-hides the amendment sheet.
[9 empty] | Year 0 | Year 1 | Year 2 | Year 3 | Total
Capital Expenses
|  |  | Internal | [5 empty] | 17640 | 0 | 0 | 0 | 17640
|  |  | External | [5 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Future Cost Commitments | [5 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Total Capital Expense | [5 empty] | 17640 | 0 | 0 | 0 | 17640
Operational Expenses
|  |  | Internal | [5 empty] | 0 | 0 | 0 | 0 | 0
|  |  | External | [5 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Future Cost Commitments | [5 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Total Operational Expense | [5 empty] | 0 | 0 | 0 | 0 | 0
| Total Cost | [7 empty] | 17640 | 0 | 0 | 0 | 17640
Internal
| Business Unit | Staff |  |  | Effort (Days) | Resources | % CapEx | Rate | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total | Resource Task | Development |  | Incremental OpEx $ | Total CapEx | Total OpEx
| Business | [15 empty] | Testing
| Business | SME |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | Implementation |  | 0 | 0 | 0
|  | BA |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | Req/Specs/Maturing backlog stories |  | 0 | 0 | 0
|  | UAT |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | Other |  | 0 | 0 | 0
IT Technology
| Development | Java |  |  | 0 | 1 | 95% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | .Net |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Profile |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | User Experience Design |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | User Experience Development |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | (Insert others as needed) |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
| Technology Services | IT Architecture |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Configuration Manager |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT-Dev JAVA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - .NET |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - Profile |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Portfolio Services |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Release Coordination |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Data Services Development | DS ETL Development |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Database Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | DS QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Data Modeling |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Reporting |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | PSFT Development |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | PSFT QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | SQL Development Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Transactional Database Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Transactional Data Modeling |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
IT Infrastructure
| Application Services | Core Banking |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Deposits |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Integration, Administrative |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Lending |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Service Desk |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Communications | Networks |  |  | 3 | 1 | 100% | 630 | 1890 |  |  |  | 1890 | 0 | 1890 |  |  |  | 0 | 1890 | -1890
|  | Telephony |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Database Services | Database (e.g. Oracle, SQL) |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Data Warehouse Prod Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Financial, Analytics |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Infrastructure Services | Access Governance |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Asset Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Capacity Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Continuity |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Performance Validation |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Service Quality |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Supplier Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Operations | Command Center |  |  | 2 | 1 | 100% | 630 | 1260 |  |  |  | 1260 | 0 | 1260 |  |  |  | 0 | 1260 | -1260
|  | Desktop Services |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Desktop Strategy |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Problem Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Security | Physical Security |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Security Infrastructure |  |  | 5 | 1 | 100% | 630 | 3150 |  |  |  | 3150 | 0 | 3150 |  |  |  | 0 | 3150 | -3150
| Server Infrastructure | Environments |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Storage and SAN |  |  | 10 | 1 | 100% | 630 | 6300 |  |  |  | 6300 | 0 | 6300
|  | Unix |  |  | 8 | 1 | 100% | 630 | 5040 |  |  |  | 5040 | 0 | 5040
|  | Wintel |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
IT Project Administration
|  | BSA |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | PM/ Scrum Master |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Sub-Total Internal Costs |  |  |  | 28 |  |  |  | 17640 | 0 | 0 | 0 | 17640 | 0 | 17640 |  |  |  | 0 | 6300 | -6300
External
| Category | Item |  |  | # of Units | Fixed Fee | CapEx % | Unit Cost | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total
| Software License | Perpetual / Subscription |  |  | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0
|  | First Year Maintenance |  |  | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Skill Types
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Java
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | .Net
| Hardware | Temporary SAN Space DE and MN |  |  | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Profile
[5 empty] | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | QA
[5 empty] | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Configuration Management
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Environments Analyst
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Wintel
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | IT Security
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | App Support
| Services | Strategic Group | Skill Type | Resource Type | [12 empty] | Database Developer | Developer
|  | Infrastructure | Java | Infrastructure | 0 | 0 | 95% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Telecom | Developer
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Supplier Specific Consultant | Developer
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | BSA | QA
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | Project Manager | Developer
| Marketing | Additional Marketing Costs | [6 empty] | 0 |  |  |  | 0 | 0 | 0 |  | ScrumMaster | Infrastructure
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | ETL | Infrastructure
[17 empty] | Data Modeler | Infrastructure
[17 empty] | Cognos | Infrastructure
| Sub-Total External Costs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other
Other
Other
Future Cost Commitments | [17 empty] | Developer
| Category | Item |  |  | # of Units / People | Fixed Fee / Bonus | CapEx % | Estimated Salary | Year 0 | Year 1 | Year 2 | Year 3 | CapEx $ | OpEx $ | Total
| Resources | New FTEs (required to support project) |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Developer
Developer
| Maintenance |  |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Infrastructure
Other
| Sub-Total External CapEx Costs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Brokerage Costs
Project Charter | [13 empty] | ING DIRECT Confidential
| Program Manager: | Karen Grose
Investment Sybase IQ Upgrade and Device Size Change
Cost Summary | [11 empty] | To specify additional year spend, expand columns I-L using the plus sign above column M.
[7 empty] | Year 0 | Year 1 | Year 2 | Year 3 | Total
Capital Expenses
|  | Internal |  |  |  |  | 228060 | 0 | 0 | 0 | 228060
|  | External |  |  |  |  | 332810.9243 | 0 | 0 | 0 | 332810.9243
|  | Future Cost Commitments |  |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Capital Expense |  |  |  |  | 560870.9243 | 0 | 0 | 0 | 560870.9243
Operational Expenses
|  | Internal |  |  |  |  | 0 | 0 | 0 | 0 | 0
|  | External |  |  |  |  | 52602 | 0 | 0 | 0 | 52602
|  | Future Cost Commitments |  |  |  |  | 21400 | 22042 | 22703.26 | 23384.3578 | 89529.6178
|  | Total Operational Expense |  |  |  |  | 74002 | 22042 | 22703.26 | 23384.3578 | 142131.6178
| Total Cost | [5 empty] | 634872.9243 | 22042 | 22703.26 | 23384.3578 | 703002.5421
Internal
| Business Unit | Staff | Effort (Days) | Resources | % CapEx | Rate | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total |  | Incremental OpEx $ | Total CapEx | Total OpEx
| Development | Back-office | 10 | 1 | 100% | 630 | 6300 |  |  |  | 6300 | 0 | 6300 |  | 0 | 0 | 0
|  | DEV DBA | 12 | 1 | 100% | 630 | 7560 |  |  |  | 7560 | 0 | 7560 |  | 0 | 0 | 0
|  | SQL | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Systems Analyst | 10 | 1 | 100% | 630 | 6300 |  |  |  | 6300 | 0 | 6300 |  | 0 | 0 | 0
|  | Systems Architect | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Web | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Web Services | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | (Insert others as needed) | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| QA | Automation | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Back-office | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Performance | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Strategic Quality Analyst | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | System Testing | 40 | 1 | 100% | 630 | 25200 |  |  |  | 25200 | 0 | 25200 |  | 0 | 0 | 0
|  | Web | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Web Services | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | (Insert others as needed) | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| IT | App Svc Inv | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Business Continuity | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | DB Services | 100 | 2 | 100% | 630 | 126000 |  |  |  | 126000 | 0 | 126000 |  | 0 | 0 | 0
|  | Network Services | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Security | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Wintel, Unix, SAN | 30 | 1 | 100% | 630 | 18900 |  |  |  | 18900 | 0 | 18900 |  | 0 | 0 | 0
|  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| Program/Project Management | Project Manager/ Scrum Master | 60 | 1 | 100% | 630 | 37800 |  |  |  | 37800 | 0 | 37800 |  | 0 | 0 | 0
|  | Deployment Manager | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| Sub-Total Internal Costs | Total Internal Costs | 262 |  |  |  | 228060 | 0 | 0 | 0 | 228060 | 0 | 228060 |  | 0 | 0 | 0
External
| Category | Item | # of Units | Fixed Fee | CapEx % | Unit Cost | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total
| Software License | IQ 3 Prod Licenses | 3 | 0 | 100% | 36720 | 110160 |  |  |  | 110160 | 0 | 110160
|  | Tax for IQ 3 Prod Licenses | 1 | 0 | 100% | 10465.2 | 10465.2 |  |  |  | 10465.2 | 0 | 10465.2
|  | Sybase IQ Enterprise 15.3 - DT CPU license | 4 | 0 | 100% | 11016 | 44064 |  |  |  | 44064 | 0 | 44064
|  | Tax for IQ 4 Dev Licenses | 4 | 0 | 100% | 4186.08 | 16744.32 |  |  |  | 16744.32 | 0 | 16744.32
| Hardware | P750 2 dual 4 core and extra NIC 128 GB Mem | 2 | 0 | 100% | 72996.94 | 145993.88 |  |  |  | 145993.88 | 0 | 145993.88
|  | Tax for P750s (MN no tax for DE) | 1 | 0 | 100% | 5383.5243 | 5383.5243 |  |  |  | 5383.5243 | 0 | 5383.5243
| Services | Shipping servers for repurposing | 4 | 0 | 0% | 5500 | 22000 |  |  |  | 0 | 22000 | 22000
|  | Tax for shipping | 1 | 0 | 0% | 2090 | 2090 |  |  |  | 0 | 2090 | 2090
|  | IQ Standard Suppot for prod licenses | 3 | 0 | 0% | 9504 | 28512 |  |  |  | 0 | 28512 | 28512
|  | Sales Tax for IQ Prod Standard Support | 1 | 0 | 0% | 2708.64 | 2708.64 |  |  |  | 0 | 2708.64 | 2708.64
|  | IQ Standard Support for Dev licenses | 4 | 0 | 0% | 2851.2 | 11404.8 |  |  |  | 0 | 11404.8 | 11404.8
|  | Sales Tax for IQ Dev Standard Support | 1 | 0 | 0% | 1083.456 | 1083.456 |  |  |  | 0 | 1083.456 | 1083.456
| Sub-Total External CapEx Costs |  | 29 | 0 |  |  | 385412.9243 | 0 | 0 | 0 | 332810.9243 | 52602 | 385412.9243
Future Cost Commitments
| Category | Item | # of Units / People | Fixed Fee / Bonus | CapEx % | Unit Cost / Salary | Year 0 | Year 1 | Year 2 | Year 3 | CapEx $ | OpEx $ | Total
| Maintenance | IBM P750 16-way HW/SW maint/support | 2 | 0 | 0% | 10700 | 21400 | 22042 | 22703.26 | 23384.3578 | 0 | 21400 | 89529.6178
| Sub-Total External CapEx Costs |  | 2 | 0 |  |  | 21400 | 22042 | 22703.26 | 23384.3578 | 0 | 21400 | 89529.6178

## AMD1 Costs (hidden)
Project Charter | [14 empty] | ING DIRECT Confidential
Investment Sybase IQ Upgrade and Device Size Change
Cost Summary | [13 empty] | To specify additional year spend, expand columns I-L using the plus sign above column M. For Office 2003 Users: To amend the cost section, unhide the "Cost - Amendment 1" sheet by selecting the Format menu, opening the Sheet sub-menu, and selecting unhide. For Office 2010 Users: Right clicking on any tab and selecting unhide brings up a sub-menu of hidden worksheets. Select AMD 1 Costs un-hides the amendment sheet.
[9 empty] | Year 0 | Year 1 | Year 2 | Year 3 | Total
Capital Expenses
|  | Internal | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | External | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | Future Cost Commitments | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | Total Capital Expense | [6 empty] | 0 | 0 | 0 | 0 | 0
Operational Expenses
|  | Internal | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | External | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | Future Cost Commitments | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | Total Operational Expense | [6 empty] | 0 | 0 | 0 | 0 | 0
| Total Cost | [7 empty] | 0 | 0 | 0 | 0 | 0
Internal | [16 empty] | Development
| Business Unit | Staff |  |  | Effort (Days) | Resources | % CapEx | Rate | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total | Resource Task | Testing |  | Incremental OpEx $ | Total CapEx | Total OpEx
Implementation
| Business | [15 empty] | Req/Specs/Maturing backlog stories
| Business | SMEs |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | Other |  | 0 | 0 | 0
|  | BA |  |  | 0 | 1 |  | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | UAT |  |  | 0 | 1 |  | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
IT Technology
| Development | Java |  |  | 0 | 1 | 95% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | .Net |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Profile |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | User Experience Design |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | User Experience Deveopment |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | (Insert others as needed) |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[5 empty] | 0 | 1 |  | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Technology Services | IT Architecture |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Configuration Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT-Dev JAVA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - .NET |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Dev - Profile |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | IT Portfolio Services |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Release Coordination |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Data Services Development | DS ETL Development |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Database Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | DS QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Data Modeling |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | DS Reporting |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | PSFT Development |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | PSFT QA |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | SQL Development Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Transactional Database Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Transactional Data Modeling |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
IT Infrastructure
| Application Services | Core Banking |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Deposits |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Integration, Administrative |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Lending |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Service Desk |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Communications Infrastructure | Networks |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Telephony |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Database Services | Database (e.g. Oracle, SQL) |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Data Warehouse Prod Support |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Financial, Analytics |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Infrastructure Services | Access Governance |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Asset Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Capacity Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Continuity |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Performance Validation |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Service Quality |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Supplier Management |  |  | 0 | 1 |  | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Operations | Command Center |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Desktop Services |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Desktop Strategy |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Problem Management |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
| Security | Physical Security |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Security Infrastructure |  |  | 0 | 1 |  | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Server Infrastructure | Environments |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Storage and SAN |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Unix |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0
|  | Wintel |  |  | 0 | 1 | 100% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| IT Project Administration | [7 empty] | 0
|  | BSA |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  | Skill Types |  | 0 | 0 | 0
|  | PM/ Scrum Master |  |  | 0 | 1 | 0% | 630 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Sub-Total Internal Costs | Total Internal Costs |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Java |  | 0 | 0 | 0
.Net
Profile
External | [16 empty] | QA
| Category | Item | Asset Tag |  | # of Units | Fixed Fee | CapEx % | Unit Cost | Year 0 | Year 1 | Year 2 | Year 3 | Total CapEx $ | Total OpEx $ | Total |  | Configuration Management
| Software License | Perpetual / Subscription |  |  | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Environments Analyst
|  | First Year Maintenance |  |  | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Wintel
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | IT Security
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | App Support
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | BSA | Developer
| Hardware | Servers |  |  | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | ScrumMaster | Developer
|  | Networking/Telephony |  |  | 0 | 0 | 100% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | ETL | QA
|  | Other |  |  | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | Data Modeler | Developer
|  | Non-Capitalized Hardware | [6 empty] | 0 |  |  |  | 0 | 0 | 0 |  | Cognos | Infrastructure
|  | (insert others as needed) | [6 empty] | 0 |  |  |  | 0 | 0 | 0 |  | Database Developer | Infrastructure
|  | (insert others as needed) | [6 empty] | 0 |  |  |  | 0 | 0 | 0 |  | Telecom | Infrastructure
| Services | Strategic Group | Skill Type | Resource Type | [12 empty] | Supplier Specific Consultant | Infrastructure
[5 empty] | 0 | 0 | 95% | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  | Other
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  | Other
[5 empty] | 0 | 0 | 0% | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  | Other
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | Developer
| Marketing | Additional Marketing Costs | [6 empty] | 0 |  |  |  | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | Developer
| Sub-Total External Costs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other
Future Cost Commitments
| Category | Item |  |  | # of Units / People | Fixed Fee / Bonus | CapEx % | Estimated Salary | Year 0 | Year 1 | Year 2 | Year 3 | CapEx $ | OpEx $ | Total
| Resources | New FTEs (required to support project) |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance |  |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total External CapEx Costs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Financial Model
Project Charter | [6 empty] | ING DIRECT Confidential
| Investment Sybase IQ Upgrade and Device Size Change | Financial Model
Cost Summary
|  | Year 0 | Year 1 | Year 2 | Year 3 | Total
Capital Expense
| Internal | 245700 | 0 | 0 | 0 | 245700
| External | 332810.9243 | 0 | 0 | 0 | 332810.9243
| Future Committed Costs | 0 | 0 | 0 | 0 | 0
| Subtotal CapEx | 578510.9243 | 0 | 0 | 0 | 578510.9243
Operational Expense
| Internal | 0 | 0 | 0 | 0 | 0
| External | 52602 | 0 | 0 | 0 | 52602
| Future Committed Costs | 21400 | 22042 | 22703.26 | 23384.3578 | 89529.6178
| Subtotal CapEx | 74002 | 22042 | 22703.26 | 23384.3578 | 142131.6178
| Total Costs | 652512.9243 | 22042 | 22703.26 | 23384.3578 | 720642.5421
| Cumulative Costs | 652512.9243 | 674554.9243 | 697258.1843 | 720642.5421 | 720642.5421
Benefit Summary
|  | Year 0 | Year 1 | Year 2 | Year 3 | Total
Cost Reduction
| Reduction in New FTE Growth |  |  |  |  | 0
| Existing Cost Reduction |  |  |  |  | 0
| Future Cost Avoidance |  |  |  |  | 0
| Total Cost Reduction |  | 0 | 0 | 0 | 0
Revenue Generation
| Generated Revenue |  |  |  |  | 0
| Total Revenue Generated |  | 0 | 0 | 0 | 0
| Total Benefits |  | 0 | 0 | 0 | 0
| Cumulative Benefits |  | 0 | 0 | 0 | 0
Benefit Assumptions
Financial Summary
| Discount Rate | 18%
|  | 0 | 1 | 2 | 3
Un-discounted
| Discount Factor | 1 | 1 | 1 | 1
| Costs | 652512.9243 | 22042 | 22703.26 | 23384.3578
| Benefits |  | 0 | 0 | 0
| Annual Cash Flow | -652512.9243 | -22042 | -22703.26 | -23384.3578
| Cumulative Benefit-Cost | -652512.9243 | -674554.9243 | -697258.1843 | -720642.5421
Discounted
| Discount Factor | 1 | 1.18 | 1.3924 | 1.643
| Costs | 652512.9243 | 18679.661 | 16305.1278 | 14232.4421
| Benefits |  | 0 | 0 | 0
| Annual Cash Flow | -652512.9243 | -18679.661 | -16305.1278 | -14232.4421
| Cumulative Benefit-Cost | -652512.9243 | -671192.5853 | -687497.7132 | -701730.1553
| Net Present Value | -701730.1553
| Discounted ROI | -100%
| Payback in Years | After Year 3

## Risk Scorecard
Project Risk Analysis
General Project Risks
What is the Charter Type? | Project |  |  | Comments:
What is the Project Type? | Maintenance and Upgrades
What is the project budget? | >500K
What is the expected Internal Labor cost? | <250K
What are the number of unique business areas impacted/working on this effort? | 4 or More Business Areas |  | Proceed to Cross Functional Estimation
What are the number of unique sprint teams impacted/working on this effort? | 1 to 3
What is the expected duration of the project? | 1 to 3 Sprints
Are all impacted teams (including third parties if applicable) utilizing Agile/Kanban? | Yes
Is the Project, Scope, Deliverable, and Success Criteria clearly defined | Understood by all impacted areas
Is the Scope clearly defined | Understood by all impacted areas
Are the Deliverables clearly defined | Understood by all impacted areas
Is Project Success Criteria clearly defined | Understood by all impacted areas
| Next Step | Cross Functional Estimation
Regulatory/Finance/Technology Risk |  |  |  |  | DR Classifications
What is the IRM classification for this application? (A1, A2, A3, A4); | A3 | Notify SprintTeamRaptor2@ingdirect.com |  |  | A1
Will this project result in the usage, storage and/or transmitting of PII (Personally Identifiable Information)/NPI (Nonpublic Personal Information)? See PII/NPI definition below | Yes | Notify IRMProjects@ingdirect.com Notify: ITSecurityInfrastructure@ingdirect.com |  | This is an upgrade of the Sybase IQ software for DSS. While DSS stores PII information this is not a new data warehouse we are upgrading the database management system software to a new maintenance version. | A2
Will this project impact SOX applications? | No |  |  |  | A3
Will this project have a technical compliance impact (regulatory requirements)? | No |  |  |  | A4
Does this project involve any Financial Transactions (e.g. a new fee item, new expense item, a new product enhancement, etc..). | No
Will this project result in any potential financial reporting changes (e.g. Head Office Reports)? | No
Will this project have potential incompatibilities within current desktop, platforms, or internally customized applications? | No
Are we early adopters of the technology utilized in this project? | No
Does the skill set exist internally to develop and/or support technology supported in this charter? | Yes
Vendor Risks
Will this Service Provider/Vendor be providing a key business process, or will they be an integral part of a day to day business function? | No
Will this Vendor receive, use, store and/or transmit PII (Personally Identifiable Information)/NPI (Nonpublic Personal Information)? See PII/NPI definition below? | No
Definitions and SLAs
PII (Personally Identifiable Information)/NPI (Nonpublic Personal Information) | Click Down Arrow for PII List

## Variables (hidden)
Charter Type | Sprint Team Size | Project Type |  | Internal Labor cost
1 to 3
Project | 4 or More | Improve Business Processes |  | <250K
Research - Proof of Concept / RFP/ RFI |  | Attract and Retain New Customers |  | >250K
New Implementation/Third Party Integration |  | Increase the Use of Information/Analytics
Facilities Request |  | Capacity and Continuity
Creates New Products or Services
|  | Support Security, Regulation, and/or Compliance | SOX
| Number of Sprint Teams | Maintenance and Upgrades
| None |  | No
| 1 to 3 |  | Calyx - inlcudes ARTA
| 4 to 6 | Methodologies | Profile Anyware
| 6 or more | Yes | SARA
|  | No, Waterfall | Transact
Project Type by team |  | No, Other | BoNY
Development Only |  |  | Collect Anywhere
Infrastructure Only |  |  | IDEA - includes AWD
Data Services Only |  |  | SASSy
Steel-Thread |  |  | SBO
Website - Transactional Servers
Number of Business Units Working with Project |  |  | Mortmenu
Orange Data Warehouse
1 Business Area |  |  | FEDLine Advantage
2 to 3 Business Areas |  |  | Quantative Risk Management - QRM
4 or More Business Areas |  |  | TPG
|  | New Application | Polypaths
Units |  | No | Wire Automation Systems
1 to 3 |  | Yes, Internal Business Application/Site (i.e. PTO)
4 to 6 |  | Yes, Internal Customer Support (i.e. Sassy)
7 to 10 |  | Yes, External Accessible Application/Site (i.e. secure.ingdirect.com)
above 10
YN |  | Duration
Yes |  | 1 to 3 Sprints
No |  | 4 or More Sprints
Project Scope, Deliverables, and Success Criteria
Not well defined
Defined but not well understood by IT
Understood by all impacted areas |  | Charter Type1
Budget |  | Project
Research - Proof of Concept / RFP/ RFI
<75K |  | New Implementation
>75K & <250K |  | Third Party Integration
>250K & <500K |  | Facilities Request
>500K |  | Charter Type2
PII |  | Infrastructure
Click Down Arrow for PII List |  | New Implementation
First Initial + Last Name (or alias) |  | Charter Type3
Maiden Name
Mother’s Maiden Name |  | Third Party Integration
Street Address |  | Development
Email Address |  | Upgrade/Maintenance
Date of Birth
Place of Birth
Race/Religion
Social Security Number (SSN)
Digital Identity (CIF, Saver ID, Account Number, PIN, PassMark Image, and biometric identifiers)
Credit Card Number/Credit History (and other financial information including transactions)
SQAs
Telephone Numbers (Mobile, Business and Personal)
Driver’s License Number/Vehicle Registration Number
Passport Number
Taxpayer Identification Number (TIN)
Fingerprints/Medical Information
Employment/Education/Criminal Information
Internet cookie information (times users visit a site, types of transactions, etc…)
Persistent Static Internet Protocol (IP) Address that is Linked to Customers
Persistent Static Media Access Control (MAC) Address that is Linked to Customers
Lists or groupings that were created using PII
On its own - Infrasructre, Dev, Datawarehouse Hardware/Software Upgrade = Proceed to estimatation but if impact is large below may need to change to Procced to Cross Functional Estmiation

## $Risks_NotImplemented (hidden)
Project Charter | [7 empty] | ING DIRECT Confidential
| New Risk | Is a risk that this project produces.
| Existing Risk | Is a risk that the bank currently has, and that this project mitigates
Risk Mitigation
| Type of Risk | Risk | Response / Solution to Risk | Size of the impact | What is impacted | Likilhood of occurance | Does this project mitigate the risk? | If so, to what extent
| Exisiting | <risk> | <response / solution> | <impact scale> | <affects> | <probability> | <mitigates risk> | <extent of mitigation>
This section of the Charter Template has not been approved for use by the project governance committee. It is not implemented and should not be used.

## $Export (hidden)
Investment Sybase IQ Upgrade and Device Size Change |  | Upload on Save? | No
General |  |  | http://cache/personal/rbouchoux/projectportfolio/Project%20Charters/
Risks | #ERROR! | Risks to the Project | http://cache/personal/rbouchoux/projectportfolio/Project%20Charters%20%20Risks/
Investment Sybase IQ Upgrade and Device Size Change
InternalEffort | #ERROR! | 89 | http://cache/personal/rbouchoux/projectportfolio/Project%20Charters%20%20Internal%20Effort/
Investment Sybase IQ Upgrade and Device Size Change
ExternalCosts | 94 | 115 | http://cache/personal/rbouchoux/projectportfolio/Project%20Charters%20%20External%20Costs/
Investment Sybase IQ Upgrade and Device Size Change
Future Committed Costs
This section of the Charter Template has not been approved for use by the project governance committee. It is not implemented and should not be used.